## Sheet1
Iteration | Pair and Task |  | Pair and Task |  | Pair and Task
| Pair | Task Component | Pair | Task Component | Pair | Task Component
Semester 1
1 | Akshay, Nikhil | Research on use of Android and App development technology | Sarvani, Sujit | Research on P2P and feasibility of Encryption Techniques | Utkarsh, Taranvir | Research on server-side technology and cloud server research
2 | Nikhil, Sarvani | Detailed Requirement Specifications for Deliverable 1 | Sujit, Utkarsh | Functional and Technical Architectures | Taranvir, Akshay | Project Development Plan
3 | Akshay, Sujit | P2P communicaiton Proof of Concept | Sarvani, Taranvir | Android Application Proof of Concept | Utkarsh, Nikhil | Map API, Infrastructure Setup
4 | Sarvani, Utkarsh | Preparing thin slice of Android App, Map API | Taranvir, Akshay | Database Design – Local and Cloud, Continuous Integration | Nikhil, Akshay | Preparing thin slice of P2P Development
5 | Utkarsh, Akshay | Finalizing thin slice of P2P Mesh | Taranvir, Nikhil | Finalizing thin slice of Map API, Android | Sarvani, Sujit | Finalizing thin slice of Database Design
6 | Taranvir, Sarvani | P2P Communication Core | Nikhil, Akshay | Maps – Routing and Matching | Sujit, Utkarsh | Authentication and Security
7 | Akshay, Sarvani | Application development | Taran, Sujit | Server – Side API | Utkarsh, Nikhil | P2P – Messaging and Chat
8 | Akshay, Sujit | P2P Services | Nikhil, Sarvani | App Development - UI | Utkarsh, Taranvir | App Development - Core
9 | Akshay, Taranvir | App Development - Core | Nikhil, Utkarsh | App Development - UI | Sujit, Sarvani | P2P Services
10 | Akshay, Utkarsh | App Development - UI & Mock Acceptance Tests | Nikhil, Sujit | App Development - Core | Taranvir, Sarvani | P2P Services
11 | Akshay, Sujit | Server-Side Development | Nikhil, Sarvani | App Development - Core | Utkarsh, Taranvir | Map – Routing and Filtering
12 | Akshay, Nikhil | Server – Side Development | Sujit, Taranvir | App Development & Mock Acceptance Tests | Utkarsh, Sarvani | Map – Routing and Filtering
13 | Akshay, Sarvani | Map – Routing and Filtering | Sujit, Nikhil | P2P Services | Utkarsh, Taranvir | App Development
14 | Akshay, Taranvir | Integration Testing | Sujit, Utkarsh | User Acceptance Testing | Sarvani, Nikhil | Bug Fixing & Mock Acceptance Tests
15 | Akshay, Nikhil | Bug Fixing | Sujit, Sarvani | Production Testing | Sarvani, Taranvir | Bug Fixing
Semester 2 (Change pairs every two weeks)
16 | Akshay, Nikhil | Isolating the devices on P2P since it is currently visible to anyone on Wifi Direct | Sarvani, Sujit | Communication of multiple devices using P2P | Utkarsh, Taranvir | Building an offline map with tiles and navigation using Graphhopper
17 | Nikhil, Sarvani | Exploring the DNS - SD approach and build the P2P module | Sujit, Utkarsh | Research on MQTT & Mock Acceptance Tests | Taranvir, Akshay | Offline Route Calculation using Graphhopper
18 (No significant work was possible as 4 of the members were travelling back home) | Akshay, Sujit | Resolving the bugs in the offline map | Sarvani, Taranvir | Research and try tools to successfully follow the pair programming paradigm | Utkarsh, Nikhil | Set up integration methods to be used while working from home
19 | Sarvani, Utkarsh | User Interface | Taranvir, Akshay | Integrating the output of Geocoding component into maps | Nikhil, Akshay | Integration of Peer communication module: convert Kotlin to Java
20 | Utkarsh, Akshay | User Interface | Taranvir, Sujit | Geocoding in Maps | Sarvani, Nikhil | Integration of Peer communication module & Mock Acceptance Tests
21 | Nikhil, Utkarsh | Integration of Geocoding on UI | Taranvir, Akshay | Maps & Mock Acceptance Tests | Sujit, Sarvani | P2P Communication
22 | Akshay, Sarvani | Documentation and Integration | Taran, Sujit | Documentation and Server Communication | Utkarsh, Nikhil | Documentation and User Interface